RouteX

PROJECT PLAN

Company Profitability Management System

COSC 70: Software Engineering I

Prepared for: Redeemed Route Logistics Inc.

Prepared by: RouteX Project Team

Project period: August 10 to December 4, 2026

Revision 1.0 | Date of issue: October 16, 2026

Draft for review. Unconfirmed costs, financial rules, and implementation details are identified as pending.

# Document Control

| Item | Details |
| --- | --- |
| Project name | RouteX: Company Profitability Management System |
| Client | Redeemed Route Logistics Inc. |
| Project manager | Louiza Joy C. Beñares (role listed in SWOT) |
| System analyst | Jelene C. Punongbayan (role listed in SWOT) |
| Quality assurance | Marc Rancel R. Bongalos (role listed in SWOT) |
| Status | Draft for review; client decisions remain pending |

# Planning Basis and Assumptions

Primary scope source: Letter of Agreement (LOA). Operational problems and team roles are informed by the SWOT Analysis. Document structure follows the supplied Project Plan template.

User-confirmed constraints: cloud-hosted web app, existing computers and internet, basic computer skills among end users, a small but unspecified budget, and three student team members.

Project period remains August 10 to December 4, 2026 per the LOA. Active development is planned to begin October 19, 2026. Earlier project time is treated as planning/requirements work only if supported by the team's actual records; actual status must be confirmed.

Maintenance and support should last one month after final client acceptance and turnover, based on the user's clarification. The LOA must be amended to state this consistently.

Specific hosting provider pricing, budget ceiling, team weekly availability, actual completed work, and final financial rules have not been supplied. They are not invented in this plan.

RouteX is for post-delivery records and profitability analysis. It is not live GPS tracking, live dispatch, a full accounting replacement, or a full payroll system.

# Executive Summary

RouteX is a proposed cloud-hosted web application for Redeemed Route Logistics Inc. It centralizes completed-delivery records and related financial information, supports retrieval of Proof of Delivery (POD) documents, and provides delivery-, truck-, and company-level profitability views. It responds to issues identified in the SWOT Analysis, including fragmented records, manual trip reporting, missing or incomplete POD files, limited subcontracted-truck visibility, and insufficient automated profitability analysis.

The proposed differentiator is profitability traceability: management can move from a company-level result to a truck, then to the deliveries and expense entries that contribute to the result. A related completeness cue can flag missing PODs or required financial information. These enhancements should be confirmed with the client and implemented only if they fit the agreed scope and deadline.

# 1. The Problem Domain

## 1.1 Statement of the Problem

The SWOT Analysis describes a lack of centralized records, reliance on group chats and manual trip reports, difficulty finding delivery documentation, limited visibility into subcontracted trucks, and insufficient automated cost and profitability analytics. Rising fuel costs increase the importance of understanding delivery and company results. RouteX addresses recordkeeping, retrieval, documentation, and profitability visibility. It does not independently solve dispatch coordination, delayed collections, or truck breakdowns.

## 1.2 Background and Rationale

The company operates owned and subcontracted trucks and serves a broad area. Earlier project context indicates approximately six owned trucks and around fifty subcontracted units, including four- and six-wheeler vehicles; these figures should be reconfirmed before being treated as formal constraints. A centralized, browser-based system fits the stated preference to use existing computers and avoid new client hardware.

## 1.3 Objectives

Centralize records: Organize truck, client, employee/crew, completed-delivery, delivery-expense, company-expense, compensation-summary, and POD records.

Improve retrieval: Search and filter records by plate number, delivery ID, driver/helper, client, transaction date, and date range.

Record completed deliveries: Maintain delivery details and financial entries after completion and upload/retrieve POD documents; no live GPS or live dispatch.

Provide profitability visibility: Present delivery-, truck-, and company-level results distinctly, based on agreed financial rules and without deducting the same expense twice.

Generate reports: Provide organized, printable operational and financial reports and approved profitability metrics.

Ensure secure access: Use authentication, role-based permissions, activity logs, and administrative functions.

## 1.4 Significance and Scope

Expected benefits are faster record retrieval, a consistent delivery/POD history, clearer truck and company financial performance, improved visibility into incomplete records, and more traceable management decisions.

### In scope for the first release

Completed-delivery records, relevant timestamps, client/truck/crew associations, revenue and applicable delivery expenses.

Fleet, client, employee/crew, and subcontractor records needed for delivery and profitability views.

Finance-managed company expense records using confirmed categories.

HR-managed compensation summaries, without full payroll processing.

POD upload and retrieval; basic missing-document cue if approved.

Global search, date filters, dashboard summaries, delivery/truck/company profitability, reports, authentication, role permissions, and activity logging.

### Out of scope unless separately approved

Live GPS tracking, live dispatch, route optimization, telematics, or new GPS hardware.

Customer portal, online booking, or customer-facing tracking.

Full accounting replacement, tax filing, statutory payroll calculations, attendance, payslips, or bank payments.

Third-party integrations, predictive maintenance, or complex overhead allocation.

Financial policies not confirmed by the client.

# 2. Project Organization

## 2.1 External Interfaces

| Stakeholder / interface | Interaction |
| --- | --- |
| President / management | Reviews profitability and reports; validates requirements and accepts the system. |
| Operations | Records completed deliveries, crew/truck assignments, and POD documents. |
| Finance | Records and categorizes expenses; reviews financial summaries. |
| HR | Maintains employee records and compensation summaries. |
| Cloud hosting/database | Hosts app, database, and private POD storage; provider and plan to be selected after price/limit review. |
| Existing computers and internet | Access RouteX through a modern browser; no new hardware assumed. |

## 2.2 Internal Structure

| Team member | Role listed in SWOT | Responsibilities to confirm |
| --- | --- | --- |
| Louiza Joy C. Beñares | Project Manager | Schedule, coordination, client communication, decision/scope log, acceptance coordination. |
| Jelene C. Punongbayan | System Analyst | Requirements, workflow and data model, role matrix, client requirement validation. |
| Marc Rancel R. Bongalos | Quality Assurance | Test plan/cases, defect tracking, calculation verification, regression testing, UAT support. |

The SWOT roles do not explicitly identify a dedicated developer. The team must assign implementation ownership for frontend, backend/database, deployment, and code review, and confirm weekly availability. The plan does not assume additional staff.

## 2.3 Department Responsibilities

| Role | Responsibilities |
| --- | --- |
| Operations | Record completed deliveries; link truck, client and crew; enter approved delivery financials; upload/retrieve POD; correct records when authorized. |
| Finance | Record company expenses, use approved expense categories, maintain dates/amounts/descriptions/supporting documents, review financial entries. |
| HR | Maintain employee records and compensation summaries for client-approved periods and rules. |
| President / management | Review company/truck/delivery results, search records, view/print reports, make decisions. |
| System administrator | Manage accounts, roles, and access settings; review logs. Admin status should not automatically grant financial-edit permissions. |
| Project team | Design, develop, test, document, deploy, train, and resolve in-scope defects. |

## 2.4 Deliverables

Approved requirements and financial-rule decision log.

System architecture, ERD, role matrix, and key screen flows.

Deployed RouteX web application and database.

Delivery, fleet, financial records, compensation summaries, search, profitability, reports, and access control.

POD workflow and completeness cue if approved.

Test plan, results, defect log, and UAT sign-off.

User guide, technical documentation, training, deployment notes, and data export/turnover package.

# 3. Review of Existing Alternatives

This is a preliminary desk-based comparison of product categories, not a hands-on product audit. Feature tiers, current pricing, Philippine compliance fit, and availability should be verified before any purchasing decision.

| Alternative | Primary fit | Potential gap to validate | RouteX positioning |
| --- | --- | --- | --- |
| Excel / spreadsheets | Low-cost manual records and calculations. | Manual consolidation, version conflicts, and weaker linked-record traceability. | Centralized related records with traceable financial results. |
| QuickBooks Online | General accounting and financial reporting. | Exact fit for plate-based delivery lookup, crew assignments, and POD workflow needs verification. | Focused operational profitability view, not an accounting replacement. |
| TruckingOffice | Trucking operations/accounting. | Verify the exact workflow, plan, and regional suitability against the client's needs. | Tailored company-to-truck-to-delivery drill-down. |
| Rigbooks | Trucking bookkeeping and cost analysis. | Verify support for this client's categories, HR summaries, PODs, and local requirements. | Benchmark for trucking-specific cost visibility. |
| Fleetio | Fleet and vehicle management. | Its main focus differs from company profitability and delivery financial records. | Keep fleet data sufficient for profitability; avoid full maintenance scope. |

RouteX should not claim competitors lack profitability functions. Its differentiator is a tailored traceability path from company result to truck, delivery, and source expense records, paired with POD completeness cues.

# 4. Development Approach

## 4.1 Method

Use an iterative, incremental approach with weekly internal reviews and scheduled client checkpoints. Build end-to-end workflows in priority order, validate financial logic before broad reporting, and test each increment.

Requirements elicitation: confirm workflows, expense categories, financial formulas, permissions, and acceptance criteria.

Data-first design: finalize relationships between deliveries, trucks, crew, expenses, compensation summaries, PODs, and users.

Incremental implementation: complete a working record workflow before adding more screens and polish.

Risk-based QA: prioritize calculations, expense uniqueness, access control, POD retrieval, and data integrity.

Usability checks: use plain labels, minimal required fields, validation, and brief training for users with basic computer skills.

## 4.2 Rationale

With three student team members, a small unspecified budget, and limited active development time, a focused MVP reduces integration risk and allows the team to defer low-priority polish rather than sacrificing financial accuracy or UAT.

## 4.3 Proposed Technology Stack

| Layer | Technology | Constraint / rationale |
| --- | --- | --- |
| Application | Next.js 15 App Router | One web app; no separate backend service. |
| Language/UI | TypeScript, React, Tailwind CSS, shadcn/ui, Lucide React | Reusable UI and type checks. |
| Server logic | Next.js Server Actions and Route Handlers | Authorization enforced server-side. |
| Database | PostgreSQL via Supabase | Relational links fit the data model. |
| Authentication | Auth.js, proposed | Validate integration with selected hosting and Supabase before commitment. |
| File storage | Supabase Storage | Private POD files with authorized access. |
| Hosting | Vercel, proposed | Check current limits, backups, data handling, and recurring cost. |
| Tools | Git, npm | Collaboration and change history. |

Architecture constraints from prior project decisions: one Next.js app, no Prisma, and no separate backend app. Do not expose service-role secrets to the browser. Confirm the proposed Auth.js/Supabase setup in a small technical spike before building the full application.

# 5. System Design

## 5.1 Functional Requirements

| ID | Function | Requirement |
| --- | --- | --- |
| FR-01 | Authentication | Users can sign in/out securely. |
| FR-02 | Role access | Users only access permitted functions and records. |
| FR-03 | Delivery records | Authorized Operations users create, view, and update completed deliveries. |
| FR-04 | Relationships | A delivery links to a client, truck, and one or more crew members. |
| FR-05 | Delivery financials | Store revenue, approved additional charges, and delivery-attributable expenses. |
| FR-06 | POD | Upload/retrieve POD linked to delivery; private access by default. |
| FR-07 | Fleet | Maintain plate, vehicle type, ownership, status, and subcontractor association where applicable. |
| FR-08 | Expenses | Finance records expense date, amount, category, description, and optional delivery/truck association. |
| FR-09 | Compensation | HR maintains summaries under approved periods/rules; not a full payroll engine. |
| FR-10 | Search | Search by plate, delivery ID, client, crew, and date range. |
| FR-11 | Profitability | Display delivery-, truck-, and company-level results under approved rules. |
| FR-12 | Traceability | Navigate from company result to truck, deliveries, and source expense records. |
| FR-13 | Reports | View/print/export agreed operational and financial reports. |
| FR-14 | Dashboard | Summarize selected operational and financial metrics by period. |
| FR-15 | Audit | Log important record and account actions with actor/time where appropriate. |
| FR-16 | Validation | Validate required fields, identifiers, amounts, and sensible date relationships. |
| FR-17 | Completeness cue | Flag missing PODs or required financial fields if approved. |

## 5.2 Non-functional requirements

Usability: plain labels, clear error messages, consistent forms, and minimal steps.

Security: server-side authorization, least privilege, protected secrets, private POD storage, and role tests.

Privacy: handle personal and financial data in line with the LOA's reference to RA 10173; do not claim legal compliance without review.

Integrity: use decimal-safe numeric fields for money and retain links needed for traceability.

Reliability: document data export and backup procedures and test them before turnover.

Compatibility: support current desktop browsers and responsive layouts; a dedicated mobile app is not in scope.

Maintainability: centralize financial formulas so dashboard and reports do not implement different versions.

Performance: verify with representative test data; no numeric SLA is stated in the source documents.

## 5.3 Modules and Submodules

| Module | Core submodules / functions |
| --- | --- |
| Dashboard | Company overview, revenue/expense summary, profitability snapshot, delivery summary. |
| Delivery Management | Completed delivery records, details/timestamps, revenue/charges, delivery expenses, crew assignment, POD, history. |
| Fleet Management | Truck registry, vehicle type, ownership/status, subcontractors, delivery assignment history. |
| Financial Management | Operational, administrative, compliance/government and miscellaneous expenses; compensation summaries; expense history. |
| Profitability Analysis | Delivery, truck, and company profitability; margin analysis; company → truck → delivery → expense drill-down. |
| Search | Global search, plate/truck, delivery, client/crew, and date filters. |
| Reports | Delivery activity, revenue, delivery expenses, company expenses, compensation summaries, profitability, print/export. |
| User and Access Management | Accounts, roles, permissions, activity logs, administration. |

## 5.4 Financial logic and unresolved rules

Financial rules are only partially confirmed. Until the client approves them, profitability calculations must be labeled provisional and should not be presented as official accounting results.

Delivery result = recorded delivery revenue minus the expenses approved for that delivery.

Truck result = approved results for deliveries associated with that truck during the selected period, plus truck-level costs only if the client explicitly defines them as part of this metric.

Company result = all applicable company revenue minus all applicable expenses, including delivery-related and non-delivery expenses, with each underlying expense deducted once.

A record may appear in multiple reports, but its presence in a report does not create a second expense.

Confirm how salary, allowance, cash advances, subcontractor costs, maintenance, registration, insurance, additional drops, overtime, demurrage, partial-hour charges, and overhead should be treated.

## 5.5 Proposed ERD entities

The initial relational model is expected to include Users, Clients, Employees, Subcontractors, Trucks, Deliveries, DeliveryCrew assignments, Delivery timestamps, ExpenseCategories, Expense records, Compensation summaries, and POD documents. Final relationships depend on approved expense and compensation rules. In particular, do not create separate duplicate expense entries simply because Finance or HR also needs a summary view.

# 6. Project Timeline

The LOA's overall period is August 10 to December 4, 2026. The user clarified that active development begins Monday, October 19, 2026, and that UAT must be completed before the December 4 deadline. The following is a proposed compressed schedule, not evidence that earlier tasks have been completed.

| Phase | Dates | Work | Exit criteria |
| --- | --- | --- | --- |
| Requirements and decision closure | Aug 10–Oct 16 (status to verify) | Planning, LOA/SWOT review, requirements, unresolved decision list. | Team records actual completion and outstanding decisions. |
| Core development | Oct 19–Nov 13 | Foundation, auth, core records, POD, Finance/HR records, search, first profitability flow. | Core workflow works end-to-end. |
| Integration and internal QA | Nov 16–20 | Cross-module tests, role tests, financial reconciliation, defect fixes. | UAT candidate is stable; no known critical defects. |
| Client UAT | Nov 23–25 | Operations, Finance, HR, and management test agreed scenarios. | Client feedback and acceptance issues documented. |
| Fixes and retesting | Nov 26–30 | Resolve in-scope UAT issues and rerun regression tests. | Critical/high-impact defects resolved or formally accepted as known limitations. |
| Training, deployment, turnover | Dec 1–4 | User orientation, production deployment, documentation, data export, sign-off. | Acceptance and turnover completed by target date. |

This schedule is tight. It assumes timely client feedback and no major scope changes. If the current project status differs, rebaseline with the client rather than treating past dates as completed.

## 6.1 Gantt Chart

| Workstream | Aug 10–Oct 16 | Oct 19–Nov 13 | Nov 16–20 | Nov 23–25 | Nov 26–30 | Dec 1–4 |
| --- | --- | --- | --- | --- | --- | --- |
| Planning / requirements | ● |  |  |  |  |  |
| Core development |  | ● |  |  |  |  |
| Integration / internal QA |  |  | ● |  |  |  |
| Client UAT |  |  |  | ● |  |  |
| Fixes / retesting |  |  |  |  | ● |  |
| Training / deployment / turnover |  |  |  |  |  | ● |

## 6.2 Work Breakdown Structure

| WBS | Work package | Output |
| --- | --- | --- |
| 1.0 | Project coordination | Schedule, status tracking, decision/risk log, scope control. |
| 1.1 | Requirements | Workflows, requirements, financial-rule decisions, acceptance criteria. |
| 1.2 | Feasibility / alternatives | Alternative comparison and hosting-cost check. |
| 2.0 | System design | ERD, architecture, role matrix, screen flows. |
| 3.0 | Application foundation | Repository, environment, auth, layout, authorization. |
| 3.1 | Operational records | Clients, employees, trucks, subcontractors, deliveries, crew, timestamps, POD. |
| 3.2 | Financial records | Expense categories/entries, compensation summaries. |
| 3.3 | Search and analysis | Filters, dashboard, profitability drill-down, reports. |
| 4.0 | Quality assurance | Test cases, calculation reconciliation, permissions, regression. |
| 5.0 | Acceptance and turnover | UAT, defect resolution, deployment, training, documentation, export. |

# 7. Budget Allocation

The available budget is described as small, but no ceiling is specified. Therefore, a defensible peso total cannot yet be stated. The plan prioritizes free development tools, existing computers, and a minimal cloud configuration, subject to verification of current service limits and pricing.

## 7.1 Estimated Costs

| Item | Estimate status | Budget control |
| --- | --- | --- |
| Development tools | ₱0 assumed initially | Use free/open-source tools where practical; verify licensing. |
| Existing computers / internet | No incremental purchase assumed | Actual recurring internet cost is unknown. |
| Cloud hosting | Unpriced; verify current plan | Check production usage, limits, deployment needs, and upgrade cost. |
| Database / POD storage | Unpriced; usage-dependent | POD storage/bandwidth may create recurring charges; set file limits. |
| Custom domain | Optional, unpriced | Use a provider subdomain for MVP if acceptable. |
| Training / documentation | Team time | No paid training assumed. |
| Contingency | Pending budget ceiling | Do not commit to recurring costs without client approval. |

## 7.2 Total Projected Budget

Total projected cash budget: pending. Before deployment, the team must confirm the budget ceiling, hosting/database provider, storage limits, backup/export options, expected usage, recurring payer, and what happens if a free tier is exceeded. Do not present free-tier use as guaranteed production capacity.

# 8. Risk Management

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Unconfirmed financial rules | High | Log decisions; approve worked examples before final calculations. |
| Double-counted salary/allowance/expense | High | Use one underlying financial record or explicit linkage; test against hand calculations. |
| Compressed active-development schedule | High | Prioritize MVP, assign coding owners, weekly review, defer cosmetic features before testing. |
| Cloud cost / free-tier limit | High | Verify current pricing/limits, monitor storage, document export, approve any paid plan. |
| Missing or inaccessible POD | High | Private storage, delivery linkage, upload validation, completeness cue, export test. |
| User entry errors | Medium | Plain-language forms, validation, defaults, quick guide, task-based training. |
| Unauthorized financial-data access | High | Server-side authorization, least privilege, private files, audit logs, role tests. |
| Poor historical data | Medium | Agree import scope; clean and validate sample data before bulk entry. |
| Late client feedback | High | Schedule decision checkpoints and log impact on scope/date. |
| Scope creep | High | Keep GPS, dispatch, full payroll/accounting, and complex allocation out of scope unless formally approved. |

# 9. Testing and Acceptance

## 9.1 Testing approach

Unit tests for calculation functions, validation, and date/amount handling.

Integration tests for delivery/truck/crew, expenses, compensation, POD, and user relationships.

Role tests for Operations, Finance, HR, management, and administrator access.

POD tests for upload, retrieval, invalid files, missing documents, and unauthorized access.

Search/report tests for plate, delivery ID, client, crew, date ranges, empty results, and representative data volume.

Manual reconciliation of profitability outputs against client-approved worked examples.

Usability checks with users who have basic computer skills.

Regression testing after fixes and before production deployment.

## 9.2 Minimum acceptance criteria

Authorized Operations user can create and retrieve a completed delivery.

Delivery records link correctly to truck, client, and assigned crew.

Authorized users can upload/retrieve POD files; private files are not exposed publicly.

Finance can create and retrieve expenses using approved categories.

HR can maintain agreed compensation summaries without unsupported full-payroll features.

Search supports plate number, delivery ID, client, crew, and date range in agreed test scenarios.

Delivery, truck, and company results match approved test examples and no expense is deducted twice.

Agreed reports can be viewed and printed/exported.

Unauthorized access is blocked and important actions are logged.

Client UAT is documented, critical defects are resolved or formally accepted, and training/documentation/turnover are complete.

# 10. Deployment, Training, and Turnover

## 10.1 Deployment

Select cloud plans after checking pricing, usage limits, private storage, backup/export, and data-handling requirements.

Keep secrets out of source control and separate development and production configuration where practical.

Apply database migrations and access policies before loading client data.

Use synthetic/anonymized data during testing; use real client data only with authorization and safeguards.

Run a deployment checklist for access control, financial calculations, POD access, export/backup, and account setup.

Verify core workflows after deployment and deliver the agreed data export and documentation.

## 10.2 Training

| Audience | Training topics |
| --- | --- |
| Operations | Completed delivery entry, truck/crew assignment, POD upload/retrieval, search, incomplete-record checks. |
| Finance | Expense entry/categories, supporting details, expense reports, approved financial rules. |
| HR | Employee records and compensation summaries, pay-period handling under approved rules. |
| Management | Date filters, company-to-truck-to-delivery drill-down, reports, source-record traceability. |
| Administrator | Accounts/roles, logs, access issues, documented export/backup procedure. |

## 10.3 Turnover package

Deployed application and user accounts.

User guide and technical documentation.

Final ERD, architecture overview, configuration notes, and secret-free environment-variable inventory.

Test results, UAT record, known limitations, and accepted unresolved items.

Client data/database export and documented export/backup procedure.

Maintenance instructions consistent with the amended LOA.

# 11. LOA Conflicts and Required Clarifications

| LOA location | Issue | Recommended action |
| --- | --- | --- |
| Section 3, page 2 vs Section 4.6, page 3 | Section 3 states six months of maintenance/support; Section 4.6 contains the contradictory wording “six two (2) to three (3) weeks” and then says 2–3 weeks. User clarified the intended period is one month. | Amend both sections to state one month from final acceptance and turnover; remove the conflicting durations. |
| Section 3, page 2 | Acceptance and turnover wording is repeated in two consecutive paragraphs, with different support references. | Consolidate into one clear acceptance/turnover paragraph. |
| Opening date vs project timeline | LOA date is October 15, 2026; project timeline starts August 10, 2026. User clarified the project began August 10, but active development begins October 19. | This is not necessarily a contradiction if work was authorized/planned earlier. Clarify in the project plan that the overall project started Aug 10 and active development starts Oct 19; ensure the LOA dates reflect the parties' intent. |
| Section 2, page 2 | Deadline remains December 4, 2026, leaving about seven weeks from active development start for development, testing, UAT, fixes, training, and turnover. | Preserve the contractual deadline unless both parties approve a written change. Prioritize MVP and protect the UAT/fix window. |
| Sections 4.5 and 4.1 | Provider retains core software IP; client receives deployed system, data export, manuals, and technical documentation. Ongoing hosting account ownership and recurring-cost payer are not explicit. | Confirm who owns/administers hosting and database accounts and who pays recurring costs after turnover. |
| Section 6.2 | Changes must be made in writing and formally agreed by both parties. | Use written approval for changes to scope, schedule, budget, or financial rules. |

# 12. Open Decisions Before Financial Features Are Finalized

Confirm what counts as revenue and how additional drops, overtime, demurrage, waiting-time fees, and partial hours are calculated.

Confirm whether fuel, toll, allowance, driver/helper compensation, and subcontractor payments are attributed to individual deliveries.

Confirm treatment of salary, cash advances, allowances, contributions, insurance, registration, maintenance, and truck expenses in company profitability.

Confirm whether truck-level costs are shown separately or included in truck profitability, and whether overhead allocation is required.

Confirm expense categories and who can create, edit, approve, or reverse financial entries.

Confirm role permissions and whether financial records need an approval workflow.

Confirm the budget ceiling, cloud provider/account owner, and recurring-cost payer.

Confirm actual task status as of October 19 and assign development responsibilities among the three students.

# References and Source Basis

RouteX Letter of Agreement, uploaded document. Used for project objectives, scope boundaries, timeline, responsibilities, data security, IP/turnover, and maintenance wording.

RouteX SWOT Analysis, uploaded document. Used for the problem domain, risks/opportunities, and named student roles.

4. PROJECT PLAN.docx, uploaded template. Used for the expected Project Plan sections.

Previously discussed RouteX requirements and user clarifications in this conversation. Used for proposed modules, cloud hosting, basic end-user skill level, small unspecified budget, active development start of October 19, 2026, one-month maintenance, and profitability traceability idea.

Preliminary alternative-product research discussed earlier. Comparisons are qualitative and require verification of current pricing and regional suitability.